**2025-2027 SPIL Timeline**

**September 2023**

* SPIL Committee begins to discuss possible topics for the next SPIL
* Workgroups are formed.

**October 2023**

* Workgroups meet to discuss desired outcomes (SMART Goal creation for SPIL)
* SPIL Chair assigns conveners for each workgroup after soliciting volunteers.

**November 2023**

* SPIL workgroups meet and begin drafting goals, objectives, timelines, outcomes to include in SPIL draft.

**December 2023**

* SPIL workgroups meet and begin drafting goals, objectives, timelines, outcomes to include in SPIL draft.

**January 2024**

* SPIL workgroups meet and begin drafting goals, objectives, timelines, outcomes to include in SPIL draft.

**February 2024**

* SPIL workgroups submit final goal language to Carrie by 2/23/24 (if possible). SILC Staff will incorporate it into the draft SPIL document.

**March 2024**

* Draft SPIL document finalized and reviewed at March Full Council Meeting (March 5-7 in Sacramento)

**April 2024**

* SPIL Hearings (Bay Area) April 2, 2024 (PM)
* SPIL Hearings (Southern California) April 12, 2024 (AM)
* SPIL Committee works to incorporate feedback from hearings into SPIL Draft

**May 2024**

* SPIL Committee votes to approve final draft of the SPIL at May SPIL Committee meeting.
* Executive Committee votes to approve final draft of the SPIL at May Executive Committee meeting.

**June 2024**

* SILC staff to work with ILC ED’s to obtain signatures (allow 2 weeks).
* SILC Staff to obtain SILC Chair signature (allow 1 week).
* SILC staff to submit final technical amendment 2024 SPIL to ACL by June 30, 2023.

**July 2024-October 2024**

* SILC staff will work with ACL on any necessary corrections or changes;
* As necessary will schedule public hearings or SPIL Committee review/approval.

**October 2024**

* 2025-2027 SPIL goes into effect on October 1, 2024.