**2025-2027 SPIL Timeline**

**September 2023**

* SPIL Committee begins to discuss possible topics for the next SPIL
* Workgroups are discussed.

**October 2023**

* Begin to form workgroups (if SILC members do not volunteer, a workgroup will be assigned).
* SPIL Chair assigns conveners for each workgroup after soliciting volunteers.
* Workgroups meet to discuss desired outcomes (where do we want to be in 3 years as the CA IL Network?)

**November 2023**

* SPIL workgroups meet to continue discussions
* SPIL workgroups begin drafting goals, objectives, timelines, outcomes to include in SPIL draft.

**December 2023**

* SPIL workgroups meet and continue drafting goals, objectives, timelines, outcomes to include in SPIL draft.

**January 2024**

* SPIL workgroups meet and continue drafting goals, objectives, timelines, outcomes to include in SPIL draft.

**February 2024**

* SPIL workgroups submit final goal language to Carrie by 2/29/24. SILC Staff will incorporate it into the draft SPIL document.

**March 2024**

* Draft SPIL document finalized and reviewed at March Full Council Meeting (March 5-6)

**April 2024**

* SPIL Hearings Virtual
* SPIL Hearings Virtual
* SPIL Committee works to incorporate feedback from hearings into SPIL Draft

**May 2024**

* SPIL Committee votes to approve final draft of the SPIL at May SPIL Committee meeting.
* Executive Committee votes to approve final draft of the SPIL at May Executive Committee meeting.

**June 2024**

* SILC Staff work to obtain DSE Director signature (allow 3 weeks)
* SILC staff to work with ILC ED’s to obtain signatures (allow 2 weeks).
* SILC Staff to obtain SILC Chair signature (allow 1 week).
* SILC staff to submit final technical amendment 2024 SPIL to ACL by June 30, 2024.

**July 2024-October 2024**

* SILC staff will work with ACL on any necessary corrections or changes;
* (As necessary will schedule public hearings or SPIL Committee review/approval.)

**October 2024**

* 2025-2027 SPIL goes into effect on October 1, 2024.